## Sheet1
Id | WeekStarting | Participants Scheduled | Participants Enrolled | AA Controls with Polyps | CA Controls with Polyps | AA Controls without Polyps | CA Controls without Polyps | AA Totals | CA Totals | Next Week Goal | Challenges Solution Notes
1 | 06/09/2025 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | there are a few different reasons we are unable to consent patients we have identified as potential candidates. some come in with diabetic issues, and nurses don't allow us to draw blood. Sometimes during the procedure, physicians determine whether or not it's safe to collect samples for our study, depending on bleeding, patients' reactions to anesthesia etc. some further delays in the OR, or surgeries beginning earlier than scheduled, makes it difficult to catch other patients who come in for their colonoscopies (or no show). We see a combination of these factors every week, and with 1 coordinator, it's difficult to make changes to make this more efficient.
2 | 06/16/2025 | 12 | 5 | 2 | 1 | 1 | 1 | 3 | 2 | 12 | there are a few different reasons we are unable to consent patients we have identified as potential candidates. some come in with diabetic issues, and nurses don't allow us to draw blood. Sometimes during the procedure, physicians determine whether or not it's safe to collect samples for our study, depending on bleeding, patients' reactions to anesthesia etc. some further delays in the OR, or surgeries beginning earlier than scheduled, makes it difficult to catch other patients who come in for their colonoscopies (or no show). We see a combination of these factors every week, and with 1 coordinator, it's difficult to make changes to make this more efficient.
3 | 7/1 | 20 | 17 | 4 | 4 | 5 | 3 | 9 | 8 | 12 | Awaiting pathology results for one CA patient. Current numbers are: AA Polyp 80 No polyp 73 unknown 10 CA Polyp 30 No polyp 29 unknown 2
4 | 07/17/2025 | 18 | 10 | 2 | 1 | 4 | 1 | 8 | 2 | 3 | 07/17/2025 - 07/25/2025 Awaiting pathology results for 1 AA and 1 CA
5 | 07/18/2025 | 100 | 35 | 8 | 5 | 18 | 3 | 27 | 8 | 12 | These numbers are representative of consents from 7/18 - 8/29 AA no polyp 18 polyp 8 unknown 1 CA no polyp 3 polyp 5